## Slide 1: District Utility Program Meeting
District 5
October 17, 2023
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 3: This meeting is being recorded
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 4: Welcome
Before we begin, let’s have a brief safety moment.
Virtual Attendees
Unmute yourself or use your chat box if you are in an emergency situation.
In-Person Attendees
Emergency Exits
Tornado Shelter
911 Caller
AED Location
Restrooms
Notes: NDOT Utility Coordinator (In-person safety briefing)
HDR (Kristen, Amanda or Alyssa) (Virtual safety briefing)

## Slide 5: Agenda
Introductions
Utility Program Updates
Construction Activities vs. Utility Conflicts
Construction Projects Review
  Outstanding 2023 Construction Projects
  2024 Construction Projects
  2025 Construction Projects
Questions & Wrap Up
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 6: Introductions
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 7: Introduce Yourself
Introduce yourself and share:
Name
Organization
Role
Favorite Pizza Topping
In-Person Attendees
Please go around the room and introduce yourself.
Virtual Attendees
Please type the information in the chat box.
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 8: Utility Program Updates
Notes: Jamie Mikkleson

## Slide 9: Key Outcome
To improve utility coordination from Design through Construction.
Notes: Jamie Mikkleson

## Slide 10: Improvement Emphasis
Communication during planning and construction
Improved utility data collection and plan presentation
Construction schedule coordination
Notes: Jamie Mikkleson

## Slide 11: Ndot utility section
Notes: Jamie Mikkleson

## Slide 12: Utilities Organization Structure
Kyle Keller
Katie Acevedo
Katharine Fischer
Don Horton
Rhett Robinson
Dave Hansen
Curt Yager
Districts 1 & 8
Districts 2 & 3
District 4
Districts 5, 6, & 7
Notes: Jamie Mikkleson

## Slide 13: Program level updates
Notes: Jamie Mikkleson

## Slide 14: Accommodation Policy
Sets forth guidelines & requirements for accommodating utility facilities within State Highway Property
In process of completely revamping the policy
Notes: Jamie Mikkleson

## Slide 15: Accommodation Policy
Current Step
Review & comment phase
Next Step
Implementation phase
Internal & FHWA concurrent review
Internal implementation & Stakeholder outreach
Notes: Jamie Mikkleson

## Slide 16: Policy – key changes
Depth of bury by facility type
Update casing requirements for steel pipelines
Outlines NDOT utility coordination process
Expand construction and maintenance requirements
Identifies construction plan and ‘As-Installed’ plan requirements
Addresses change in ownership and abandoned or out of service facilities
Broadband chapter
Notes: Jamie Mikkleson

## Slide 17: Project level updates
Notes: Jamie Mikkleson

## Slide 18: Conflict analysis process
Utility Company will perform Conflict Analysis​
  ​Review for conflicts with:
    Final construction – limits of construction, ROW, ditch grading
    Temporary construction – drives, access crossings, phasing
  NDOT will review analysis and work with Utility Company
If relocations are required, Utility Company will provide relocation information: ​
  Scope of work​
  Detailed cost estimate​
  Schedule of relocation work​
Notes: Jamie Mikkleson

## Slide 19: Utility questionnaire
Receive via email from NDOT Utility Coordinator
Action by Utility Company required: ​
  Review and provide information for existing facility locations​
  Review existing locations for construction conflicts, both temporary and permanent conflicts​
Transmit responses and supporting documentation back to NDOT​
NDOT will track unresponsive utility companies & continue to follow up
Notes: Jamie Mikkleson

## Slide 20: Relocation process
NDOT will review and provide comments on relocation plans and detailed cost estimate​
  Will be incorporated into the agreement
Master (Blanket) Agreement or Utility Project Agreement​
  Only if relocation is reimbursable
Letter of Authorization
  Every relocation
Notes: Jamie Mikkleson

## Slide 21: 2024 Goals
Implement Utility Accommodation Policy
Identify utility conflicts early
Coordinate utility relocations to be complete by construction start
Professional development of coordinator staff
2024 District Utility Program Meetings – October
Notes: Jamie Mikkleson

## Slide 22: Activities vs. conflicts
When we say… | Think about…
Access Crossings – Contractor ~Pipes or Temp. Bridge | Cranes and large equipment Impacts or proximity to overhead power Piling for temporary bridge
Shoo-flys – Traffic | In addition to access crossings Additional fill Impacts to pedestals, pull boxes, overhead power, etc.
Grade beam on pile | Cranes Impacts or proximity to overhead power
Over-excavation | Possibility on any project Most likely at culverts and locations of known muck
Notes: Jamie Mikkleson

## Slide 23: Activities vs. conflicts
When we say… | Think about…
Concrete Box Culverts | Sheet pile driven at wingwalls Impacts to buried lines Impacts or proximity to overhead power Temporary shoring on phased construction
Culvert Replacements – Phased construction | Potential for temporary shoring Need room (H & V) to construct end treatments
Culvert Replacements – Jacking | Large jacking pits - ~50’x100’, not shown in plans Temporary excavation down to flowline to construct Need room (H & V) to construct end treatments
Notes: Jamie Mikkleson

## Slide 24: Activities vs. conflicts
When we say… | Think about…
Temporary Roads & Drives | Can require grading and ditch work Similar impacts to permanent construction
Guardrail | Posts can impact underground facilities
Sidewalk & ADA work | Pavement removal Shallow service lines
Curb Inlets | 3 ft – 6 ft deep, in most cases Cast in place inlets require extra room for form work
Notes: Jamie Mikkleson

## Slide 25: Construction Projects Review
District 5

## Slide 26: Outstanding Construction Year 2023
The following projects will likely not be completed in 2023
Notes: Kathy Fischer or Rhett Robinson

## Slide 27: Sidney EB Rest Area Buildings (TK) (LET) Project No.: NH-80-1(169); Control No.: 51275A
Project Length: 0
Scope of Work:
  Misc.
  Grading

## Slide 28: Sidney EB Rest Area Buildings (TK) (LET) Project No.: NH-80-1(169); Control No.: 51275A
Status: Award Pending
Right-of-Way: Not Required
Traffic Impacts:
  Other
Letting Date: 7/13/2023
Construction Timing: 9/11/2023

## Slide 29: Sidney EB Rest Area Buildings (TK) (LET) Project No.: NH-80-1(169); Control No.: 51275A
Anticipated Utilities Impact:
  New Alignment
  Grading
  Culvert Extension/Replace
Anticipated Request from Utilities:
  Coordination with NDOT
  Locates
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  High West Energy, Lumen (CenturyLink)

## Slide 30: Bushnell - West Kimball Project No.: NH-80-1(196); Control No.: 51583
Project Length: 9.49
Scope of Work:
  Full Depth Pavement
  Culvert Extension/Replace
  Guardrail

## Slide 31: Bushnell - West Kimball Project No.: NH-80-1(196); Control No.: 51583
Status: Construction in Progress
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: Let
Construction Timing: In Progress

## Slide 32: Bushnell - West Kimball Project No.: NH-80-1(196); Control No.: 51583
Anticipated Utilities Impact:
  Full Depth Pavement
  Grading
  Culvert Extension/Replace
Anticipated Request from Utilities:
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Warren Air Force Base, Coaral Productions, Dalton Tele., Great Plains Comm., High West Energy, Tallgrass Energy, TRI Family Oil

## Slide 33: S. Jct. N-71 East Project No.: STP-88-1(110); Control No.: 51561
Project Length: 20.37
Scope of Work:
  Resurfacing
  Bridge Repair
  Grading

## Slide 34: S. Jct. N-71 East Project No.: STP-88-1(110); Control No.: 51561
Status: Construction in Progress
Right-of-Way: Completed
Traffic Impacts:
  Phase Traffic Control
Letting Date: 6/15/2023
Construction Timing: 8/21/2023

## Slide 35: S. Jct. N-71 East Project No.: STP-88-1(110); Control No.: 51561
Anticipated Utilities Impact:
  Guardrail
  Culvert Extension/Replace
Anticipated Request from Utilities:
  Coordination with NDOT
  Provide Existing Locations
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Lumen, North Platte NRD,Great Plains Comm., Warren Air Force Base, Viaero Fiber, OPTK Network, CHACO Energy, Enbridge, Wyrulec Co., T-Mobile/ Sprint

## Slide 36: D5 VSA Project No.: ITS-MISC-D5(1010); Control No.: 51599
Project Length: 0
Scope of Work:
  ITS/Lighting
  Grading

## Slide 37: D5 VSA Project No.: ITS-MISC-D5(1010); Control No.: 51599
Status: Construction in Progress
Right-of-Way: Completed
Traffic Impacts:
  Phase Traffic Control
Letting Date: Let
Construction Timing: In Progress

## Slide 38: D5 VSA Project No.: ITS-MISC-D5(1010); Control No.: 51599
Anticipated Utilities Impact:
  Shlder Work
Anticipated Request from Utilities:
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  AT&T, Black Hills Energy, Lumen/Century Link, Charter Comm., City of Chappell, City of Kimball, City of Sidney, Dalton Tele., Foundation Energy, Great Plains Comm., High West Energy, Highline Electric, Kinder Morgan, Nebraska Rural Electric, Nebraska PPD, Cogent Comm-T-Mobile/Sprint, Tallgrass, Viaero, Western Area Power Admn, Wheatbelt PPD

## Slide 39: Sidney Interchange Lighting Project No.: NH-80-2(116); Control No.: 51619
Project Length: 0
Scope of Work:
  ITS/Lighting
  Grading

## Slide 40: Sidney Interchange Lighting Project No.: NH-80-2(116); Control No.: 51619
Status: Construction in Progress
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: Let
Construction Timing: 10/2/2023

## Slide 41: Sidney Interchange Lighting Project No.: NH-80-2(116); Control No.: 51619
Anticipated Utilities Impact:
  Lighting
  Shlder Work
Anticipated Request from Utilities:
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  Special Provisions Required
Utilities Involved:
  City of Sidney, Gas Present, and Telephone Present, USAF Cable present

## Slide 42: Construction Year 2024
The following projects are anticipated to be let during 2024
Notes: Kathy Fischer or Rhett Robinson

## Slide 43: Chappell East (MS) Project No.: STP-30-1(139); Control No.: 51462A
Project Length: 10.11
Scope of Work:
  Resurfacing
  Full Depth Pavement
  Culvert Extension/Replace

## Slide 44: Chappell East (MS) Project No.: STP-30-1(139); Control No.: 51462A
Status: Preparing for Bid
Right-of-Way: Completed
Traffic Impacts:
  Phase Traffic Control
  Full Detour
Letting Date: 11/16/2023
Construction Timing: 6/1/2024

## Slide 45: Chappell East (MS) Project No.: STP-30-1(139); Control No.: 51462A
Anticipated Utilities Impact:
  New ROW
  Culvert Extension/Replacement
  Bridge Repair/Replacement
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
  Locates
Additional Information:
  K-Sheets Required
  Special Provisions Required
Utilities Involved:
  AT&T Comm., Black Hills Energy, City of Chappell, Highline Electric, Lumen (CenturyLink), Nebraska PPD, OPTK Networks (NebraskaLink), Wheatbelt PPD

## Slide 46: US-138 West (MS) Project No.: STP-30-1(140); Control No.: 51463A
Project Length: 10.38
Scope of Work:
  Resurfacing
  Full Depth Pavement
  Culvert Extension/Replace

## Slide 47: US-138 West (MS) Project No.: STP-30-1(140); Control No.: 51463A
Status: Preparing for Bid
Right-of-Way: Completed
Traffic Impacts:
  Phase Traffic Control
  Full Detour
Letting Date: 11/16/2023
Construction Timing: 6/1/2024

## Slide 48: US-138 West (MS) Project No.: STP-30-1(140); Control No.: 51463A
Anticipated Utilities Impact:
  New ROW
  Culvert Extension/Replacement
  Bridge Repair/Replacement
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
  Locates
Additional Information:
  K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Black Hills Energy, Kinder Morgan, Lumen (CenturyLink), Nebraska PPD, Tallgrass Energy, Wheatbelt PPD, KEBRH

## Slide 49: Watson Ranch South (MS) Project No.: STP-71-4(116); Control No.: 51018
Project Length: 9.13
Scope of Work:
  Resurfacing
  Culvert Extension/Replace
  Misc.

## Slide 50: Watson Ranch South (MS) Project No.: STP-71-4(116); Control No.: 51018
Status: Preparing for Bid
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 2/1/2024
Construction Timing: 6/1/2024

## Slide 51: Watson Ranch South (MS) Project No.: STP-71-4(116); Control No.: 51018
Anticipated Utilities Impact:
  Culvert Extension/Replacement
  Grading
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Great Plains Comm., Lumen (CenturyLink), Nebraska PPD, OPTK Networks (NebraskaLink), Panhandle Rural Electric

## Slide 52: Crawford North Project No.: STP-71-4(118); Control No.: 51185
Project Length: 11.69
Scope of Work:
  Resurfacing
  Bridge Repair
  Guardrail

## Slide 53: Crawford North Project No.: STP-71-4(118); Control No.: 51185
Status: Preparing for Bid
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 2/29/2024
Construction Timing: 6/17/2024

## Slide 54: Crawford North Project No.: STP-71-4(118); Control No.: 51185
Anticipated Utilities Impact:
  Bridge Repair/Replacement
  Guardrail
  Culvert Extension/Replacement
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Black Hills Energy, City of Crawford , Hemingford Coop Telephone Co., Lumen (CenturyLink), Mobius Comm. Co., Nebraska PPD, Northwest Rural PPD, OPTK Networks (NebraskaLink), Spring Creek Pipeline Co.

## Slide 55: Sidney - Sunol Project No.: NH-80-2(109); Control No.: 51585
Project Length: 8
Scope of Work:
  Resurfacing
  Bridge Repair

## Slide 56: Sidney - Sunol Project No.: NH-80-2(109); Control No.: 51585
Status: Preparing for Bid
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 2/29/2023
Construction Timing: 4/1/2024

## Slide 57: Sidney - Sunol Project No.: NH-80-2(109); Control No.: 51585
Anticipated Utilities Impact:
  Guardrail
  Access Crossings
  Overhead Power Line Crossing
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Black Hills Energy, Charter Comm. (Spectrum), City of Sidney, High West Energy, Lumen (CenturyLink), Tallgrass Energy, USAF –Warren AFB 90th MMX/HICS, Wheatbelt PPD

## Slide 58: Sidney WB Rest Area Parking Lot & Ramps (MS) Project No.: NH-80-2(117); Control No.: 51625
Project Length: 0
Scope of Work:
  Full Depth Pavement
  Culvert Extension/Replace
  Grading

## Slide 59: Sidney WB Rest Area Parking Lot & Ramps (MS) Project No.: NH-80-2(117); Control No.: 51625
Status: Preparing for Bid
Right-of-Way: Completed
Traffic Impacts:
  Other
Letting Date: 2/29/2024
Construction Timing: 7/8/2024

## Slide 60: Sidney WB Rest Area Parking Lot & Ramps (MS) Project No.: NH-80-2(117); Control No.: 51625
Anticipated Utilities Impact:
  New Alignment
  Grading
  Lighting
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
  Locates
Additional Information:
  K-Sheets TBD
  Special Provisions TBD
Utilities Involved:
  Lumen (CenturyLink), USAF –Warren AFB 90th MMX/HICS, Wheatbelt PPD

## Slide 61: South Dakota Line South Project No.: STP-71-4(126); Control No.: 51645
Project Length: 16.86
Scope of Work:
  Resurfacing

## Slide 62: South Dakota Line South Project No.: STP-71-4(126); Control No.: 51645
Status: Preparing for Bid
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 2/1/2024
Construction Timing: 7/22/2024

## Slide 63: South Dakota Line South Project No.: STP-71-4(126); Control No.: 51645
Anticipated Utilities Impact:
  Shoulder Work
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Golden West Telephone Co., Lumen (Century Link), Mobius Comm. Co., Spring Creek Pipeline Co.

## Slide 64: Box Butte/Sheridan Co. Line East Project No.: NH-2-1(127); Control No.: 51614
Project Length: 16.91
Scope of Work:
  Resurfacing
  Shoulder Work

## Slide 65: Box Butte/Sheridan Co. Line East Project No.: NH-2-1(127); Control No.: 51614
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 2/1/2024
Construction Timing: 5/1/2024

## Slide 66: Box Butte/Sheridan Co. Line East Project No.: NH-2-1(127); Control No.: 51614
Anticipated Utilities Impact:
  Culvert Extension/Replacement
  Shoulder Work
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  AT&T Comm., Black Hills Energy, Charter Comm. (Spectrum), City of Gordon, Great Plains Comm., Lumen (CenturyLink), Nebraska PPD, Panhandle Rural Electric, Rural Nebraska Healthcare Network, Viaero Fiber Net. (NE-CO Cell.)

## Slide 67: Sidney WB Rest Area Building Project No.: NH-80-2(92); Control No.: 51276A
Project Length: 0
Scope of Work:
  Misc.
  Grading

## Slide 68: Sidney WB Rest Area Building Project No.: NH-80-2(92); Control No.: 51276A
Status: Preparing for Bid
Right-of-Way: Not Required
Traffic Impacts:
  Other
Letting Date: 7/25/2024
Construction Timing: 10/1/2024

## Slide 69: Sidney WB Rest Area Building Project No.: NH-80-2(92); Control No.: 51276A
Anticipated Utilities Impact:
  Grading
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Lumen (CenturyLink), USAF –Warren AFB 90th MMX/HICS, Wheatbelt PPD

## Slide 70: US-385 South of Bridgeport Project No.: MISC-385-3(1025); Control No.: 51665
Project Length: 0.75
Scope of Work:
  Full Depth Pavement
  Grading
  Shoulder Work

## Slide 71: US-385 South of Bridgeport Project No.: MISC-385-3(1025); Control No.: 51665
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 7/25/2024
Construction Timing: 9/9/2024

## Slide 72: US-385 South of Bridgeport Project No.: MISC-385-3(1025); Control No.: 51665
Anticipated Utilities Impact:
  New ROW
  New Alignment
  Full Depth Pavement
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
  Locates
Additional Information:
  K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Black Hills Energy, Charter Comm. (Spectrum), City of Bridgeport, Lumen (CenturyLink), OPTK Networks (NebraskaLink), Tallgrass Energy, Wheatbelt PPD

## Slide 73: Oshkosh - I-76 Project No.: NH-80-2(112); Control No.: 51591
Project Length: 7.8
Scope of Work:
  Pavement Repairs

## Slide 74: Oshkosh - I-76 Project No.: NH-80-2(112); Control No.: 51591
Status: Award Pending
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 9/28/2023
Construction Timing: 8/1/2024

## Slide 75: Oshkosh - I-76 Project No.: NH-80-2(112); Control No.: 51591
Anticipated Utilities Impact:
  No Impacts
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  AT&T Comm., Black Hills Energy, Charter Comm. (Spectrum), Lumen (CenturyLink), Nebraska PPD, Cogent Comm. Inc (T-Mobile, Sprint), Verizon (MCI), Wheatbelt PPD

## Slide 76: Construction YEAR 2025
The following projects are anticipated to be let during 2025
Notes: Kathy Fischer or Rhett Robinson

## Slide 77: Smith Lake South (MS) Project No.: STP-250-4(103); Control No.: 51192
Project Length: 12.7
Scope of Work:
  Resurfacing
  Culvert Extension/Replace
  Misc.

## Slide 78: Smith Lake South (MS) Project No.: STP-250-4(103); Control No.: 51192
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 4/21/2025

## Slide 79: Smith Lake South (MS) Project No.: STP-250-4(103); Control No.: 51192
Anticipated Utilities Impact:
  Shoulder Work
  Grading
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  City of Rushville-Sewer, Great Plains Comm., Lumen (Century Link), Panhandle Rural Electric

## Slide 80: Lodgepole - Chappell (MS) Project No.: STP-30-1(129); Control No.: 51401
Project Length: 8.18
Scope of Work:
  Resurfacing
  Culvert Extension/Replace

## Slide 81: Lodgepole - Chappell (MS) Project No.: STP-30-1(129); Control No.: 51401
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 7/22/2025

## Slide 82: Lodgepole - Chappell (MS) Project No.: STP-30-1(129); Control No.: 51401
Anticipated Utilities Impact:
  Culvert Extension/Replacement
  New ROW
  Access Crossings
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Black Hills Energy, Charter Comm. (Spectrum), City of Chappell, Dalton Telephone Co., Lumen (CenturyLink), OPTK Networks (NebraskaLink), Cogent Comm. Inc (T-Mobile, Sprint), Village of Lodgepole, Wheatbelt PPD

## Slide 83: Bushnell - Kimball Project No.: STP-30-1(138); Control No.: 51560
Project Length: 11.43
Scope of Work:
  Resurfacing
  Grading
  Guardrail

## Slide 84: Bushnell - Kimball Project No.: STP-30-1(138); Control No.: 51560
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 6/9/2025

## Slide 85: Bushnell - Kimball Project No.: STP-30-1(138); Control No.: 51560
Anticipated Utilities Impact:
  Bridge Repair/Replacement
  Shoulder Work
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Black Hills Energy, Village of Bushnell, Charter Comm. (Spectrum), Dalton Telephone Co., High West Energy, Kimball Wind LLC, City of Kimball, Lumen (CenturyLink), Rural Nebraska Healthcare Network, Cogent Comm. Inc (T-Mobile, Sprint), Tallgrass Energy

## Slide 86: Lodgepole Area Bridges Project No.: NH-80-2(115); Control No.: 51617
Project Length: 0
Scope of Work:
  Bridge Repair

## Slide 87: Lodgepole Area Bridges Project No.: NH-80-2(115); Control No.: 51617
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 5/1/2025

## Slide 88: Lodgepole Area Bridges Project No.: NH-80-2(115); Control No.: 51617
Anticipated Utilities Impact:
  Bridge Repair/Replacement
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Black Hills Energy, Dalton Telephone Co., Lumen (CenturyLink), Wheatbelt PPD

## Slide 89: Scottsbluff Area Bridges Project No.: NH-71-3(128); Control No.: 51618
Project Length: 0
Scope of Work:
  Bridge Repair

## Slide 90: Scottsbluff Area Bridges Project No.: NH-71-3(128); Control No.: 51618
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 5/1/2025

## Slide 91: Scottsbluff Area Bridges Project No.: NH-71-3(128); Control No.: 51618
Anticipated Utilities Impact:
  Bridge Repair/Replacement
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Allo Comm., AT&T Comm., Black Hills Energy, Charter Comm. (Spectrum), City of Gering, City of Scottsbluff, Cityof Terrytown, Gering Irrigation Dist., Kinder Morgan, Lumen (CenturyLink), Nebraska PPD, OPTK Networks (NebraskaLink), Cogent Comm. Inc (T-Mobile, Sprint), Viaero Fiber Net. (NE-CO Cell.), WAPA

## Slide 92: Kimball Area Bridges Project No.: NH-71-2(114); Control No.: 51620
Project Length: 0
Scope of Work:
  Bridge Repair

## Slide 93: Kimball Area Bridges Project No.: NH-71-2(114); Control No.: 51620
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 5/1/2025

## Slide 94: Kimball Area Bridges Project No.: NH-71-2(114); Control No.: 51620
Anticipated Utilities Impact:
  Bridge Repair/Replacement
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Black Hills Energy, Charter Comm. (Spectrum), City of Kimball, Dalton Telephone Co., Great Plains Comm., Lumen (CenturyLink), OPTK Networks (NebraskaLink), Cogent Comm. Inc (T-Mobile, Sprint), Viaero Fiber Net. (NE-CO Cell.)

## Slide 95: W Jct US-385 - Chadron (MS) Project No.: NH-20-1(150); Control No.: 51616
Project Length: 3.11
Scope of Work:
  Resurfacing
  Full Depth Pavement
  Culvert Extension/Replace

## Slide 96: W Jct US-385 - Chadron (MS) Project No.: NH-20-1(150); Control No.: 51616
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 11/7/2024
Construction Timing: 7/1/2025

## Slide 97: W Jct US-385 - Chadron (MS) Project No.: NH-20-1(150); Control No.: 51616
Anticipated Utilities Impact:
  Culvert Extension/Replacement
  New ROW
  Lighting
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  Special Provisions TBD
Utilities Involved:
  Black Hills Energy, Charter Comm., City of Chadron, Dawes County 911, Great Plains Comm. , Lumen (CenturyLink), Mobius Comm., Nebraska PPD, OPTK Networks (NebraskaLink), Rural Nebraska Healthcare

## Slide 98: Lakeside East (MS) Project No.: NH-2-1(128); Control No.: 51646
Project Length: 10.55
Scope of Work:
  Resurfacing
  Pavement Repairs
  Shoulder Work

## Slide 99: Lakeside East (MS) Project No.: NH-2-1(128); Control No.: 51646
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 3/6/2025
Construction Timing: 5/1/2025

## Slide 100: Lakeside East (MS) Project No.: NH-2-1(128); Control No.: 51646
Anticipated Utilities Impact:
  Lighting
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  K-Sheets TBD
  Special Provisions TBD
Utilities Involved:
  Allo Comm., Concolidated Telco, Lumen (CenturyLink), OPTK Network (NebraskaLink), Panhandle Rural Electic Membership Assn.

## Slide 101: Burton Lake East (MS) Project No.: NH-2-1(129); Control No.: 51647
Project Length: 9.7
Scope of Work:
  Resurfacing
  Pavement Repairs
  Shoulder Work

## Slide 102: Burton Lake East (MS) Project No.: NH-2-1(129); Control No.: 51647
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 3/6/2025
Construction Timing: 5/1/2025

## Slide 103: Burton Lake East (MS) Project No.: NH-2-1(129); Control No.: 51647
Anticipated Utilities Impact:
  Culvert Extension/Replacement
  Shoulder Work
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Allo Comm., Concolidated Telco, Lumen (CenturyLink), OPTK Network (NebraskaLink), Panhandle Rural Electic Membership Assn.

## Slide 104: Morrill - Mitchell (MS) Project No.: NH-26-1(174); Control No.: 51615
Project Length: 6
Scope of Work:
  Resurfacing
  Pavement Repairs
  ITS/Lighting

## Slide 105: Morrill - Mitchell (MS) Project No.: NH-26-1(174); Control No.: 51615
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 7/7/2025

## Slide 107: Morrill - Mitchell (MS) Project No.: NH-26-1(174); Control No.: 51615
Anticipated Utilities Impact:
  No Impacts
  Shlder Work
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Allo Comm., Black Hills Energy, Charter Comm. (Spectrum), City of Mitchell, Enterprise Irr. Dist., Farmers Irr. Dist., Great Plains Comm., Lumen (CenturyLink), Roosevelt PPD, Tallgrass Energy, Village of Morrill, Western Sugar COOP

## Slide 108: West of Lodgepole - West of Chappell Project No.: NH-80-2(118); Control No.: 51627
Project Length: 9.2
Scope of Work:
  Pavement Repairs

## Slide 109: West of Lodgepole - West of Chappell Project No.: NH-80-2(118); Control No.: 51627
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 5/1/2025

## Slide 110: West of Lodgepole - West of Chappell Project No.: NH-80-2(118); Control No.: 51627
Anticipated Utilities Impact:
  No Impacts
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Black Hills, City of Chappell, Dalton Telephone, Lumen (Century Link), OPTK (Nebraska Link)

## Slide 111: Potter - Brownson Project No.: NH-80-1(203); Control No.: 51628
Project Length: 11.6
Scope of Work:
  Pavement Repairs

## Slide 112: Potter - Brownson Project No.: NH-80-1(203); Control No.: 51628
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 5/1/2025

## Slide 113: Potter - Brownson Project No.: NH-80-1(203); Control No.: 51628
Anticipated Utilities Impact:
  No Impacts
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Charter Comm, Cogent (T-Mobile, Sprint),Dalton Telephone, Lumen (Century Link), OPTK (Nebraska Link), Warren Air Force Base

## Slide 114: Wyoming Line - Bushnell Project No.: NH-80-1(204); Control No.: 51629
Project Length: 9.5
Scope of Work:
  Pavement Repairs

## Slide 115: Wyoming Line - Bushnell Project No.: NH-80-1(204); Control No.: 51629
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 5/1/2025

## Slide 116: Wyoming Line - Bushnell Project No.: NH-80-1(204); Control No.: 51629
Anticipated Utilities Impact:
  No Impacts
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Cogent (T-Mobile, Sprint), Dalton Telephone, Great Plains Comm, High West Energy, Warren Air Force Base

## Slide 117: EAST KIMBALL - POTTER Project No.: NH-80-1(205); Control No.: 51630
Project Length: 11.7
Scope of Work:
  Pavement Repairs

## Slide 118: EAST KIMBALL - POTTER Project No.: NH-80-1(205); Control No.: 51630
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 5/1/2025

## Slide 119: EAST KIMBALL - POTTER Project No.: NH-80-1(205); Control No.: 51630
Anticipated Utilities Impact:
  No Impacts
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Chaco Energy, Cogent (t-Mobile, Sprint), Charter Comm, Dalton telephone, Foundation Energy Mng, Lumen (Century Link), Hig West Energy, OTPK (Nebraska Link)

## Slide 120: In Scottsbluff (MS) Project No.: NH-STP-26-1(178); Control No.: 51635
Project Length: 12.12
Scope of Work:
  Resurfacing
  Pavement Repairs
  Bridge Repair

## Slide 121: In Scottsbluff (MS) Project No.: NH-STP-26-1(178); Control No.: 51635
Status: Planning
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 12/12/2024
Construction Timing: 4/1/2025

## Slide 122: In Scottsbluff (MS) Project No.: NH-STP-26-1(178); Control No.: 51635
Anticipated Utilities Impact:
  Shlder Work
  Grading
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Action Comm, Black Hills Energy, City of Scottsbluff, Charter Comm, Enterprise Irrigation Dist, Lumen (Century Link), Nebraska PPD, OPTK (Nebraska Link), Roosevelt PPD, Western Sugar

## Slide 123: Questions & Wrap Up
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 124: Any final Questions?
Ask them now!
If you have questions after this meeting, or would like to view more detailed project maps, please reach out to your utility coordinator.
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 125: Have a Question about a project your Utility is involved in?
Contact your district’s utility coordinator!
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 126: We need your feedback
Your valuable feedback helps these meetings – and NDOT’s utility coordination program – be better.
Use your phone’s camera to scan this QR code or use our paper survey.
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 127: Visit our Website
Visit NDOT.info/utility for more information on:
Utility accommodation
Permitting
Coordination
Project information
Reimbursements
Additional information
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 128: Thank You
Notes: HDR (Kristen, Amanda or Alyssa)